## Risk Management Plan
Risk Category | Risk | Probability of Problem | Impact | Weight of Risk (% of all impacts) | Probability * Impact $$ | Probability*Impact Score Assuming 0-3 Range Rounded to Whole Number
Technology | Level of Complexity | 10% | 5000 | 13.33% | 500 | 2
Technology | Level of Customization | 30% | 3000 | 8% | 900 | 2
Technology | Configuration Detail | 10% | 1000 | 2.667% | 100 | 1
Resource | Member Drops | 10% | 1000 | 2.667% | 100 | 1
Resource | Skill Level of Resources | 25% | 3000 | 8% | 750 | 2
Resource | Cost of Training | 10% | 1000 | 2.667% | 100 | 1
Organizational Risk | Percentage of Volunteers affected | 50% | 8000 | 21.33% | 4000 | 3
Organizational Risk | Process Change Required | 20% | 3000 | 8% | 600 | 2
Implementation | Timeline (Client Delays) | 10% | 5000 | 13.33% | 500 | 2
Implementation | Impact on Existing Systems | 80% | 7500 | 20% | 6000 | 3
| sum |  | 37500

## Risk Analysis
Instructions: Enter the weight and score for each type of risk, and the explanation for it. (only the values in blue should be entered)
Coefficient | 3.3333
Criteria | Weight | Score (0-3) | Weighted Score | 3 | 2 | 1 | 0 | Explanation
Technology Risk | 2.4 | ---- | 15 | High | Medium | Low | None
Level of Complexity | 1.3 | 2 | 8.6667 | High | Medium | Low | None | Due to the variety of implementations for increased functionality for volunteers and youth council admins.
Level of Customization required | 0.8 | 2 | 5.3333 | High | Medium | Low | None | Due to utlizing Wix, there are some limits to customization
Configuration Detail required | 0.3 | 1 | 1 | High | Medium | Low | None | Wix was chosen so it's easy for Youth Council admins to maintain, so it has a lower risk
Resource Risk | 1.4 | ---- | 7.3333 | High | Medium | Low | None
Availability of Resources | 0.3 | 1 | 1 | None Available | Some | Almost All | All Available | Free Wix platform allows for customization but at a limit, Youth Council admins are okay with changes making this a low risk.
Skill level of Available Resources | 0.8 | 2 | 5.3333 | None | Low | Medium | High | Team is used to more technical work and don't have prior experience with Wix
Cost of training per personnel | 0.3 | 1 | 1 | High | Medium | Low | None | Low risk as admins are already used to the application so not much other onboarding will be required.
Organizational Complexity | 2.9 | --- | 26.3333 | High | Medium | Low | None
Percentage of volunteer students affected | 2.1 | 3 | 21 | All units | > 50% units | < 50% units | None units | Volunteers will using be relying more on the website as main source. Admins will replace other files as this is all consolidated so higher risk.
Process Change Required | 0.8 | 2 | 5.3333 | Most/All | Some | Few | None | Volunteers will be using this website rather than utilizing other tools causing new changes.
Implementation Risk | 3.3 | ---- | 28.6667 | High | Medium | Low | None
Timeline | 1.3 | 2 | 8.6667 | > 24 months | 12 - 24 months | 3 - 12 months | 0 - 3 months | Slight risk as there is a short turnaround time to get a new website
Impact on Existing Systems | 2 | 3 | 20 | High | Medium | Low | None | Higher risk as much more traffic to this website will replace main processes.
Risk Index (0-100) | Sum = 10 |  | 77.3333
The following chart can be used to calculate Discount Rate
|  |  | Risk Index | Discount Rate
|  |  | 90 - 100 | 50%
|  |  | 80 - 89 | 40%
|  |  | 70 - 79 | 30%
|  |  | 60 - 69 | 20%
|  |  | 50 - 59 | 16%
|  |  | 40 - 49 | 14%
|  |  | 30 - 39 | 12%
|  |  | 20 - 29 | 8%
|  |  | 10 - 19 | 6%
|  |  | 0 - 9 | 4%